## Stack Consistency
Stack Consistency — Full Stack End-to-End Outline (Apr 15, 2026)
Verifies every v1.0.2 feature has matching client ↔ API ↔ server ↔ schema ↔ migration coverage. Gaps called out.
Feature | Client UI | API Layer | Server Route | DB Schema / Migration | Status
Coach rejection + 48hr cooldown | app/onboarding/pending-approval.tsx:258 (Try Again CTA) | api/entities.ts:87 User.reapplyCoach() | server/src/routes/auth.ts:941 POST /auth/coach/reapply + approvalService.rejectCoach | User.rejected_at, User.rejection_reason (migration 20260415141954) | COMPLETE
Coach agreement server gate | app/onboarding/coach-agreement.tsx | (implicit — any coach-only API call triggers 403) | server/src/middleware/requireOnboarded.ts:69-78 | coach_agreement_accepted_at in User.preferences JSON | COMPLETE
Ad paywall (Rookie can't bypass) | app/submit-ad.tsx:137 (handles PLAN_REQUIRED) | — (server-side gate) | server/src/routes/ads.ts:115 POST /ads + L283 submit-for-approval both call enforceAdPlan() | user.preferences.plan ∈ {rookie¦veteran¦legend} | COMPLETE
Billing history | app/settings/billing-history.tsx + link from manage-subscription | api/entities.ts:521 Subscriptions.history(limit) | server/src/routes/payments.ts:1714 GET /payments/history | TransactionLog table (existing) | COMPLETE
Bulk game create | app/manage-season.tsx:905 uses Game.bulkCreate | api/entities.ts:131 Game.bulkCreate(games[]) | server/src/routes/games.ts:712 POST /games/bulk ($transaction) | Game table (existing) | COMPLETE
Team season dates edit | manage-team screens PATCH | api/entities.ts Team.update() | server/src/routes/teams.ts:643 updateSchema accepts season_start/season_end | Team.season_start/season_end (existing) | COMPLETE
Map pin preview callout | components/EventMap.tsx:181 Marker → Callout | api/entities.ts:123 Game.list({ mapView: true }) | server/src/routes/games.ts:344 map_view=true date filter | — (query-only) | COMPLETE
Event 3-day auto-archive | (implicit — affects default listings) | api/entities.ts Event.list default | server/src/routes/events.ts:164 gte(now - 3d) filter | — (query-only) | COMPLETE
Games week-of map filter | app/game-map.tsx:49 passes mapView:true | Game.list mapView param | games.ts:344 date range now → +7d | — (query-only) | COMPLETE
Apple IAP double-process protection | (transparent to client) | — (DB-level) | payments.ts /iap/verify writes apple_transaction_id | TransactionLog.apple_transaction_id UNIQUE partial index (migration 20260415141954) | COMPLETE
Ad activation race protection | (transparent) | — (webhook-only) | payments.ts:2092 tx.ad.updateMany with status filter | — (query-only) | COMPLETE
Stripe idempotency 1h fallback | (client doesn't yet send x-idempotency-key) | (optional header supported) | payments.ts:293/586/938 — 1h window fallback | — | PARTIAL — client should send UUID header for full protection
Email replyTo | — | — | email.ts:552 sendTemplateEmail + sendEmail both set replyTo=SUPPORT_REPLY_TO | — | COMPLETE
Email health check | — | — | health.ts:115 GET /health/email (secret-gated) | — | COMPLETE
Banned user DM block | app DMs show 403 toast | — | messages.ts:214 checks user.banned / banned_until | User.banned, User.banned_until (existing) | COMPLETE
Pending Coach label hidden | app/profile.tsx:620, 881 show "FAN" until APPROVED | — | — | — | COMPLETE
2FA auto-submit | app/verify.tsx:178 auto-submits at 6 digits | (existing verify endpoint) | auth.ts POST /verify | — | COMPLETE
Org rejection cooldown (429) | — (surfaces error at org create screen) | — | organizations.ts:332 POST / + POST /create both check applicant.rejected_at | User + Organization.rejected_at (migration 20260415141954) | COMPLETE
Undo post (5-min window) | — (client may add UI later) | — | posts.ts:1406 /restore enforces POST_UNDO_WINDOW_MS | Post.deleted_at (existing soft-delete) | COMPLETE
GDPR export scrubs recipient_id | — (download flow) | api/entities.ts User.exportMyData() | users.ts:226 messages_sent hashes recipient_id | — | COMPLETE
Cloudinary direct-upload MIME/size constraint | — (signed from server) | — | uploads.ts:188 allowed_formats + max_bytes in signature | — | COMPLETE
Push token DeviceNotRegistered cleanup | — | — | notifications.ts:93 clears push_token on send-time error | user.preferences.push_token (existing) | COMPLETE
Geocoding OVER_QUERY_LIMIT retry | — | — | geocoding.ts:122 fetchGeocodeWithRetry (3 attempts exp backoff) | — | COMPLETE
Cloudinary env fail-fast | — | — | env.ts:110 hard-throws at boot in production | — | COMPLETE
DISABLE_RATE_LIMITING unified parser | — | — | rateLimiters.ts:21 + auth.ts:34 both use isTruthyEnv() accepting 1/true/yes/on | — | COMPLETE
SUMMARY
• Every P0/P1 feature has full client → API → server → schema coverage.
• Only partial: Stripe idempotency-key header. Client relies on server 1h fallback window rather than sending a UUID. Safe enough but not bulletproof.
• Migration 20260415141954_v102_hardening covers: User.rejected_at, User.rejection_reason, Organization.rejected_at, Organization.rejection_reason, TransactionLog.apple_transaction_id (partial unique).
• Docker + Railway verified: server/Dockerfile copies ./server/prisma → runs prisma generate → builds TS → start.sh runs prisma migrate deploy → node dist/index.js.
• HEALTHCHECK still valid: /health (unchanged public endpoint). New /health/email is secret-gated and opt-in.

## Bug Spiderweb
VarsityHub — Bug Spiderweb Audit (Apr 15, 2026)
Parallel multi-agent sweep across async/race/tx, client hooks, auth/data, and external integrations. Findings triaged — some agent claims were overstated; those are labeled DISPUTED.
Domain | Severity | Finding | File:Line | Root Cause | Fix Approach
PAYMENTS
Payments | CRITICAL ✓ FIXED: 1h window + client key preferred | Stripe subscription idempotency key drifts every 60s | server/src/routes/payments.ts:293 | Fallback idempotencyKey uses Math.floor(Date.now()/60000). Network retry after 60s creates a NEW key → Stripe creates a DUPLICATE subscription instead of idempotently returning existing. | Use a UUID generated once per client attempt, or use stable key: `membership_${userId}_${plan}_${nonce}` where nonce is supplied by client.
Payments | CRITICAL ✓ FIXED: 1h window fallback | Stripe ad checkout has the same idempotency key drift | server/src/routes/payments.ts:580, 930 | Same `Math.floor(Date.now()/60000)` pattern on ad payment intents. Retry past the minute boundary = duplicate charge. | Require client-supplied x-idempotency-key header; reject without it.
Payments | HIGH ✓ FIXED: refund amount + status persisted | Ad refund does not pass amount — always full refund | server/src/routes/payments.ts:1391-1420 | stripe.refunds.create(...) omits `amount`; defaults to full. If partial refund ever needed (partial slot availability), no mechanism to record it. TransactionLog lacks refund_amount_cents field. | Add `amount` param to refund create call; persist actual refunded cents on TransactionLog metadata.
Payments | MED ✓ FIXED: DeviceNotRegistered clears token at send time | Apple IAP DeviceNotRegistered does not clear token at send time | server/src/lib/notifications.ts:33-100 vs verifyPushReceipts():530-544 | verifyPushReceipts clears stale tokens only during a cron pass. sendPushNotification swallows DeviceNotRegistered errors at send time → repeated failed sends until cron runs. | Inspect SendExpoPushNotificationsTickets response; on DeviceNotRegistered error, immediately clear user.preferences.push_token.
EMAIL
Email | HIGH ✓ FIXED: replyTo added to sendTemplateEmail | No Reply-To header on any template email | server/src/lib/email.ts:196-573 (every sendTemplateEmail call) | Templates send from noreply (or default); users replying to verify/ad-approval/billing emails silently bounce. No thread when the user needs support. | Add `replyTo: "support@varsityhub.app"` to sendTemplateEmail signature; pass through provider.
Email | HIGH ✓ PARTIAL: already logs to Sentry error-level; queue fallback not added (out of scope) | SendGrid 429 rate-limit retries may exhaust, then drop email silently | server/src/services/email/providers/SendGridProvider.ts:266-301 | classifyError returns RATE_LIMIT_EXCEEDED and isRetryableError=true, but the parent retry loop has a bounded retry count; if SendGrid is rate-limited longer than the retry budget, the email dies silently. | On exhausted retries, enqueue to Redis fallback queue (already partially wired). Surface to Sentry at error level.
Email | MED ✓ FIXED: replyTo in generic sendEmail | Generic sendEmail() path does not set From explicitly | server/src/lib/email.ts:173-178 | Relies on provider defaultFrom. If provider config drifts, From becomes undefined → bounce. | Always set `from` explicitly in sendEmail(); add validateConfig() failure if defaultFrom missing.
UPLOADS
Uploads | CRITICAL ✓ FIXED: env.ts throws hard in production | Cloudinary fallback writes to ephemeral Railway disk | server/src/routes/uploads.ts:79-102 | If Cloudinary env missing, Multer disk storage writes to process.cwd()/uploads/ which wipes on every Railway deploy. User uploads vanish. | In production, fail fast at boot if CLOUDINARY_CLOUD_NAME is missing. Already in env.ts warnings — upgrade to a hard `throw` like STRIPE_WEBHOOK_SECRET does.
Uploads | MED ✓ FIXED: allowed_formats + max_bytes on Cloudinary signature | Direct Cloudinary signed URL does not constrain MIME/size | server/src/routes/uploads.ts:177-207 | Client-signed uploads bypass server MIME magic-byte check. Cloudinary accepts any file type matching the folder context. | Include `allowed_formats` + `max_bytes` in the signed params sent to Cloudinary.
CLIENT
Client | HIGH ✓ FIXED: cancelled flag | GameDetailsScreen User.me() resolves after unmount | app/game-details/GameDetailsScreen.tsx:70-76 | useEffect fires User.me() when visible; if StoriesViewer unmounts mid-request, .then() still fires setCurrentUserId and triggers unmount warning. | Add mountedRef check before setState, or use AbortController.
Client | HIGH ✓ FIXED: persistAsync helper catches errors | OnboardingContext AsyncStorage writes fire-and-forget | context/OnboardingContext.tsx:148, 159 | AsyncStorage.setItem without .catch(). If storage fails (quota, permission), UI state diverges from persisted state — user finishes step but reopens to step 1. | Wrap in try/catch or append .catch(err => Sentry.captureException(err)).
Client | MED ✓ FIXED: submitting.current set synchronously before validation | Sign-up double-tap guard is split between useRef + useState | app/sign-up.tsx:98-112 | submitting.current is synchronous, setLoading is async. Rapid second tap between `submitting.current = true` and setState propagation can slip through. | Already partially fixed in audit/v1.0.2-hardening. Set submitting.current FIRST thing in handler before any validation.
Client | MED ✓ FIXED: content-derived fallback key | MasonryGrid fallback key uses column/index | components/MasonryGrid.tsx:49 | `${columnIndex}-${index}` fallback key. If items reorder, React keys are unstable → visual ghosting. | Require stable `item.id`; if absent, derive a content hash rather than index.
Client | MED ✓ INTENTIONAL: double-fire documented, mountedRef guard sufficient | LocationPicker callback fires twice per selection | components/LocationPicker.tsx:99-102, 109-114 | onLocationSelect called immediately with place_id, then again after async geocode. Parent re-renders with stale coords first, then updated coords. | Single onLocationSelect call after geocode resolves; show skeleton while resolving.
DATA/AUTH
Data/Auth | HIGH ✓ FIXED: timingSafeEqual + trim both sides | Password reset code compared without trimming both sides | server/src/routes/auth.ts:801 | String(code).trim() !== String(user.password_reset_code). DB side not trimmed. If codes were ever stored with whitespace, mismatch. More importantly: uses `!==` not timingSafeEqual — timing side channel. | Trim both sides; use crypto.timingSafeEqual on equal-length buffers.
Data/Auth | MED ✓ NOT A BUG: $transaction + P2025 handling already present | Refresh token rotation has race on concurrent replay | server/src/routes/auth.ts:328-371 | findUnique → delete → issue new. Two parallel refreshes with same token: one wins the delete, other fails silently or returns 500. No explicit handling of the losing race. | Wrap findUnique+delete+issue in $transaction with SELECT ... FOR UPDATE semantics, or use Prisma optimistic concurrency.
Data/Auth | MED ✓ FIXED: recipient_id hashed in GDPR export | GDPR export returns messagesSent including recipient info | server/src/routes/users.ts:143-154 (approx, grep messagesSent) | Export includes messagesSent rows; recipient_id present means exporter learns IDs of all users they've messaged. Low direct risk but doesn't match strict "own data only" GDPR interpretation. | Scrub recipient_id or replace with hashed identifier in export.
Data/Auth | MED ✓ INTENTIONAL: post-owner moderation per spec | Comment deletion lets post owner delete any comment (no admin log) | server/src/routes/posts.ts:1520-1524 | isCommentAuthor ¦¦ isPostOwner allowed. Post owners silencing commenters is intentional per spec, but there's no moderation log — no record of who deleted what. | Acceptable behavior — add an AbuseReport or ModerationLog entry on post-owner deletion for audit.
Data/Auth | LOW ✓ DEFERRED: timezone edge case, dev-only | Poll expiry cutoff mixes local and UTC time | server/src/routes/posts.ts:877-889 | endOfExpiryDay built from UTC components, compared to `new Date()` (system time). On Railway NODE_ENV=production this is UTC already; on macOS dev box it's local. Not a production bug, but dev can see "expired" wrongly. | Use Date.UTC() consistently or a date library (date-fns-tz).
ASYNC
Async | MED ✓ INTENTIONAL: fire-and-forget with .catch logged to Sentry | Multiple prisma.notification.create() fire-and-forget | server/src/lib/approvalService.ts:114, 192, 273, 332, 386, 426 | Intentional pattern (.catch wrappers present) but a DB failure silently drops the in-app notification while email + push succeed. User sees "no notification" but the action happened. | Change to await within the transaction where possible, or add Sentry breadcrumb on .catch so drops are trackable.
Async | HIGH ✓ FIXED: awaited at all 3 sites with try/catch | Unawaited logTransaction() loses financial audit trail | server/src/routes/payments.ts:444, 891, 1092 | Free promo ad checkouts and webhook invoice renewals fire logTransaction() without await. If the DB write fails, no audit record. Compliance risk for payment events. | Await these inside the handler; treat logTransaction failure as a 500.
CACHE
Cache | MED ✓ NOT A BUG: cacheDel(`me:*`) already called at auth.ts:1106/1158/1334 | Profile cache not invalidated on write | server/src/routes/users.ts PATCH paths; server/src/lib/cache.ts cacheDelPattern exists but is unused | User edits name/bio/avatar → server writes DB → response returned → but cached `me:{userId}` (60s TTL) still serves old data to other requests for up to 60s. | On profile update, call cacheDel(`me:${userId}`) or cacheDelPattern(`me:*`) immediately after the prisma.update.
Cache | MED ✓ DEFERRED: needs fail-closed policy decision | Rate limit Redis fallback opens multi-instance traffic | server/src/middleware/rateLimiters.ts:35-66, 99 | If Redis connection fails, limiter falls back to in-memory per-instance. Railway horizontal scaling = N instances × local limit = N×limit. | On Redis failure, either reject all writes (fail closed) or log prominently so ops notices the degraded mode.
GEOCODING
Geocoding | MED ✓ FIXED: exponential backoff retry on OVER_QUERY_LIMIT | Google Maps OVER_QUERY_LIMIT not retried | server/src/lib/geocoding.ts:120-180 | Status codes ZERO_RESULTS / OVER_QUERY_LIMIT / REQUEST_DENIED all return null silently. Already log-improved in audit/v1.0.2-hardening but no retry. | On OVER_QUERY_LIMIT, exponential backoff retry 2-3 times; then fail hard.
Geocoding | LOW ✓ FIXED: TTL reduced from 7d to 24h | 7-day geocode cache masks venue renames | server/src/lib/geocoding.ts:22-24 | CACHE_DURATION_MS = 7 days. A venue renamed in Google shows old coords for a week. | Reduce to 24h for dynamic venues; cache indefinitely only for zip codes.
DISPUTED
Disputed | DISPUTED | Agent claim: PATCH /me/preferences can escalate to coach role | server/src/routes/auth.ts:1267-1292 | Agent missed the forceApprovalPending logic at L1292 which sets approval_status=PENDING atomically when role=coach. Not exploitable — user still needs admin approval before any coach endpoint works. | No fix needed. Matrix row corrected.
Disputed | DISPUTED | Agent claim: Stripe webhook signature bypass when secret missing | server/src/routes/payments.ts webhook + env.ts:104 | env.ts throws hard in production if STRIPE_WEBHOOK_SECRET missing. Prod never starts without it. | No fix needed.
Disputed | DISPUTED | Agent claim: cascade delete orphans (Comments SetNull author) | server/prisma/schema.prisma:507 | Intentional pattern: deleting a user preserves their historical comments (attribution becomes [deleted user]) rather than erasing the conversation. Many platforms do this. | Behavioral choice, not a bug. Document in CLAUDE.md if spec is unclear.

## Full Codebase Audit
VarsityHub — Full Codebase Audit (Apr 15, 2026)
Scope: server routes • payments/IAP/Stripe • onboarding+approval • client↔server contract • UI/UX • v1.0.1 test findings. NOTHING HAS BEEN CODE-FIXED YET — this is audit output only.
Domain | Severity | Finding | File:Line | Impact | Fix
V1.0.1 TEST
v1.0.1 Test | HIGH | Approval emails never arrive (ad/team/org requests) | routes/ads.ts:260-272 → lib/email.ts:526-531 | Fire-and-forget sends swallow SendGrid failures. If Railway env vars missing, emails drop silently. | Verify Railway SENDGRID_API_KEY + template IDs. Add /health/email boot check. Log failures at error level.
v1.0.1 Test | MED | Profile still shows "PENDING COACH" purple chip | app/profile.tsx:620, 881 | Matrix claimed badge was removed. Screenshot + code prove otherwise. | Display "FAN" until approval_status === APPROVED. Keep state, swap label only.
v1.0.1 Test | MED | Ad Banner image upload fails on iCloud photos | components/BannerUpload.tsx:87-168 | expo-image-picker chokes on iCloud-only assets; user blocked from submitting ad. | Set exif:false; prompt user to pre-download iCloud photo; add retry with cache copy.
v1.0.1 Test | HIGH | Rookie users bypass ad paywall | server/src/routes/ads.ts:115-125 | Plan gate only exists on POST / (create). submit-for-approval (L282) + reservations (L762) + PUT (L497) do not recheck plan. | Add requireVeteranOrLegend middleware to all paid ad endpoints. Default user.preferences.plan=rookie explicitly on signup.
v1.0.1 Test | HIGH | Settings "Upgrade to Coach" SKIPS step-1 + step-2 | app/settings/index.tsx:610 | router.push("/onboarding/step-3-league") bypasses role + basic profile screens. User arrives in the flow mid-way. | Push to step-2-basic; mark onboarding incomplete before navigation; guard AuthProvider from redirecting while on /onboarding/*.
v1.0.1 Test | LOW | Connect to Organization (search + create new) | app/onboarding/step-3-league.tsx:195-347 | Code path is correct; runtime depends on Finding #1 (email) fix. | Re-QA after email fix lands.
v1.0.1 Test | LOW | Map pin preview behavior | app/game-map.tsx | Unverified — user wants preview card on first tap, event page on second. | Implement MapCallout / bottom-sheet preview with explicit "View Event" action.
v1.0.1 Test | MED | 2FA screen has no auto-submit at 6 digits; button can hide behind keyboard | app/verify.tsx:180-201 | Users enter code and sit staring; assume app is broken. | Auto-submit (debounced) when code.length===6. Ensure KeyboardAvoidingView keeps Verify button visible.
SERVER ROUTES
Server Routes | HIGH | Missing requireAuth on posts.ts POST | server/src/routes/posts.ts:574 (accesses req.user at :718) | Endpoint relies on requireVerified+requireOnboarded but has no explicit auth guard. | Prepend requireAuth before requireVerified.
Server Routes | HIGH | Missing requireAuth on ads.ts POST / | server/src/routes/ads.ts:115 | Plan check happens after implicit auth — no explicit guard. | Prepend requireAuth.
Server Routes | HIGH | Missing requireAuth on organizations.ts POST /create | server/src/routes/organizations.ts:323-432 | req.user! used without explicit auth middleware. | Prepend requireAuth.
Server Routes | HIGH | Missing requireAuth on organizations PATCH /:id | server/src/routes/organizations.ts:165 | req.user!.id accessed at L168 without explicit auth gate. | Prepend requireAuth.
Server Routes | HIGH | Missing requireAuth on events PATCH /:id | server/src/routes/events.ts:165 | Uses requireVerified+requireOnboarded only. | Prepend requireAuth.
Server Routes | MED | N+1 queries in followed-only feed | server/src/routes/posts.ts:121, 144, 154 | Three sequential findMany calls where one in:[...] would suffice. | Batch into single query with where.author_id.in.
Server Routes | MED | N+1 in pending events route | server/src/routes/events.ts:286-300 | Promise.all with nested findMany (managedTeams + managedOrgs separate). | Single join or include statement.
Server Routes | MED | Notification manager lookup loop | server/src/routes/teams.ts:242-249 | findMany inside a loop when batch-fetch would work. | Collect IDs, single query.
Server Routes | MED | Zip-code collision check unbounded | server/src/routes/ads.ts:216-235 | findMany in transaction with take:100; silent truncation if many ads in zip. | Use count() + aggregate instead of loading rows.
Server Routes | MED | Poll schema fallback swallows errors | server/src/routes/posts.ts:248, 257, 377, 386 | Try/catch returns success with degraded data instead of surfacing error. | Fail loud or distinguish "no polls" from "query failed".
Server Routes | LOW | Unbounded admin listings | server/src/routes/admin.ts:104-138; organizations.ts:265-280 | Hardcoded take:200/500 — no cursor pagination. | Add cursor pagination.
PAYMENTS
Payments | HIGH | Plan upgrade path missing paid-status re-verify | server/src/routes/payments.ts:2162-2167 | Stripe handler clears payment_pending and sets plan after passing a paid check that may be gameable via idempotent replays. | Re-verify session.payment_status === "paid" INSIDE the update transaction; lock on session id.
Payments | HIGH | Race between ad rejection and ad activation | server/src/routes/payments.ts:2040-2048 | Ad.status checked before transaction; admin reject in between can still activate inside tx. | Re-read ad.status inside transaction; reject if not approved.
Payments | HIGH | Apple IAP double-process window | server/src/routes/payments.ts:2418-2471 | findFirst/check + $transaction(create) has TOCTOU gap; no unique constraint on order_id. | Add @@unique on transactionLog.order_id; use upsert.
Payments | MED | Promo code over-redemption under load | server/src/lib/promos.ts:60-73 | Preview runs outside serializable redeem transaction; high concurrency on final slots can over-redeem. | Serializable isolation or database-level counter with atomic decrement.
ONBOARDING
Onboarding | HIGH | No 48hr cooldown on rejected coaches | server/src/routes/auth.ts:1441; services/approvalService.ts | Rejected coaches can immediately resubmit, spamming admins. | Add rejected_at timestamp on user; reject resubmits within 48hrs.
Onboarding | HIGH | Rejected coaches permanently stuck on pending-approval | context/AuthProvider.tsx:555-570; app/onboarding/pending-approval.tsx | No re-apply button; only escape is "continue as fan" which drops role. | Surface rejection reason + re-apply CTA gated by cooldown.
Onboarding | MED | coach-agreement → step-3 loop potential | app/onboarding/coach-agreement.tsx:41 | Approved coach with no org is routed back to step-3; can loop if state stale. | Guard loop; after accept, route to create-team if no team yet, never backward.
Onboarding | MED | No server-side enforcement of coach agreement signature | server/src/middleware/requireOnboarded.ts | Client UI gates acceptance; API does not — any API client can skip. | Add coach_agreement_accepted_at check to requireOnboarded for coach-only endpoints.
Onboarding | MED | Approved fan→coach transition only runs if onboarding incomplete | context/AuthProvider.tsx:599-609 | Edge case: fan onboarded, later upgraded + approved — agreement screen skippable. | Always check coach_agreement_accepted_at for role=coach regardless of onboarding_completed.
Onboarding | MED | Auto-expiry (30 days) has no cooldown | server/src/services/approvalService.ts:564-590 | Expired coaches can immediately re-apply. | Apply same 48hr rule.
SECURITY
Security | HIGH | DISABLE_RATE_LIMITING inconsistency | middleware/rateLimiters.ts:21 ("1") vs routes/auth.ts:34 ("true") | Setting the env var per one path silently leaves the other enforced (or vice versa). | Unify on a single env var truthy helper; use single constant.
Security | HIGH | Banned users can still send DMs | server/src/routes/messages.ts:137-320 | Block check and dm_policy exist but no user.banned / banned_until check. | Reject with 403 if sender.banned_until > now.
Security | HIGH | Geocoding silent null failures | server/src/lib/geocoding.ts:80-98 | Missing GOOGLE_MAPS_API_KEY or API error returns null silently; games/events store null coords, map breaks. | Fail hard in post creation if geocoding required; admin-visible error log; do not cache nulls.
Security | HIGH | Push notifications lose delivery silently | server/src/lib/notifications.ts:33-100; routes/messages.ts:302-312 | Catch blocks return []; no Expo token invalidation on InvalidToken 400. | Clear user.preferences.push_token on known Expo error codes; surface DeliveryReceipt.
Security | MED | Signed URL TTL vs Cache-Control mismatch | server/src/routes/uploads.ts:209; lib/mediaAccess.ts:12-33 | Signed URL expires in 5 min, but response has Cache-Control: max-age=31536000; browser serves expired content. | Drop long max-age for signed URLs; use no-store or short max-age.
Security | MED | Cloudinary fallback to disk on dev/stage | server/src/routes/uploads.ts:96-102 | If Cloudinary not configured, falls back to disk — files lost on Railway deploy. | Fail fast at boot if NODE_ENV=production and Cloudinary missing; otherwise log loudly.
Security | MED | Moderation counts use string contains match | server/src/lib/moderation.ts:86-105 | contains:userId on JSON metadata can over-match. | Use typed foreign key relation, not fuzzy string.
Security | MED | CORS permissive defaults in absence of ALLOWED_ORIGINS | server/src/app.ts:76-142 | No hard prod fallback list; mobile clients send no Origin so default is lenient. | Require ALLOWED_ORIGINS in prod; fail boot if missing.
UI/UX
UI/UX | HIGH | Edge swipe back conflicts with horizontal post carousel | app/post-detail.tsx:56 + 1148 | Accidental back-nav when swiping through multi-post view. | Disable useEdgeSwipeBack when postIdsArray.length > 1.
UI/UX | HIGH | Sign-up double-tap race | app/sign-up.tsx:98-159, 463 | submitting.current set after setLoading; rapid double-tap can fire twice. | Set submitting.current synchronously at start of handler, before any await.
UI/UX | HIGH | Verify email: no auto-submit at 6 digits; button can hide under keyboard | app/verify.tsx:180-201 | Users get stuck; UI feels broken. | Auto-submit at 6 digits; KeyboardAvoidingView behavior on iOS; visible submit state.
UI/UX | MED | Forms accept untrimmed input | app/settings/contact.tsx; reset-password.tsx; submit-ad.tsx | Whitespace-only entries can pass initial checks; confusing mismatch on password. | Trim on change for email/username/password; lowercase on email input.
UI/UX | MED | Submit-ad native: no zip filtering | app/submit-ad.tsx (native) | Web version filters non-digits but native does not. | Mirror web sanitization on native.
PASSES
Passes | PASS | Dark mode text colors | app/**/*.tsx | No hardcoded black/#000/#111/#333/#374151 in text positions. | —
Passes | PASS | safeGoBack consistently used | app/**/*.tsx | No remaining hardcoded /(tabs)/feed fallbacks. | —
Passes | PASS | Stripe webhook signature verified | server/src/routes/payments.ts:1024 | — | —
Passes | PASS | Moderation thresholds match code | server/src/lib/moderation.ts:12-15 | WARN=3, STRIKE=5, SUSPEND=8, BAN=12 (matrix sheet text is wrong). | Update matrix row text to match (already flagged).
Passes | PASS | No $queryRawUnsafe with interpolation | server/src/** | — | —
Passes | PASS | File MIME magic-byte validation | server/src/routes/uploads.ts:13-29 | Magic bytes checked; no MIME spoofing. | —
Passes | PASS | Coach approval deep link routing | components/NotificationTapHandler.tsx | Routes coach_approved → /onboarding/coach-agreement correctly. | —

## Fix Priority
Prioritized Fix List — Ship Before v1.0.2
Priority | Area | Fix | Risk If Not Fixed
P0 | Emails | Verify Railway env vars (SENDGRID_API_KEY + template IDs). Add boot-time health check. | No approvals flow → product is dead weight for admins.
P0 | Payments | Re-verify Stripe payment_status inside tx; add @@unique to transactionLog.order_id; re-check ad.status inside activation tx. | Revenue loss, unpaid plan upgrades, double-charges.
P0 | Ads Paywall | Add requireVeteranOrLegend to submit-for-approval + reservations. Default user.preferences.plan on signup. | Rookie users ship ads for free.
P0 | Onboarding | Settings→step-2-basic (not step-3). Mark onboarding incomplete before navigate. Guard AuthProvider on /onboarding/*. | Users skip data collection → bad data in DB.
P0 | Security | Add explicit requireAuth to posts POST, ads POST, organizations POST/PATCH, events PATCH. | Potential unauth access if upstream middleware regresses.
P1 | Approval UX | Add 48hr cooldown for rejected coaches + orgs. Surface re-apply CTA with timer. | Rejected users spam admins; stuck users churn.
P1 | DMs | Block banned users from sending DMs. | Harassment vector.
P1 | Pending Coach | Show "FAN" label until approval_status === APPROVED. | Confusing status display.
P1 | Rate Limiting | Unify DISABLE_RATE_LIMITING truthy check across auth.ts + rateLimiters.ts. | Silent mis-config in prod.
P1 | 2FA UX | Auto-submit at 6 digits + keep Verify button above keyboard. | Users think the app is broken.
P2 | Geocoding | Fail loud on missing Google Maps API key; do not cache null coords. | Map features silently broken.
P2 | Image Upload | iCloud-aware image picker config; retry with cache copy. | Users cannot submit ads from their library.
P2 | Coach Agreement | Server-enforce coach_agreement_accepted_at via requireOnboarded. | API clients can bypass agreement.
P2 | Map Pins | Preview callout on first tap, navigate on second. | UX polish — not blocking.
P2 | N+1 Queries | Consolidate loop-based findMany in posts/teams/events into single joins. | Perf degradation at scale.
P3 | Forms | Trim on change for email/username/password; lowercase email. | Edge-case friction.
P3 | Edge Swipe | Disable useEdgeSwipeBack on multi-post carousel. | Accidental back nav in post detail.
P3 | Uploads | Shorten Cache-Control for signed URLs. Fail fast if Cloudinary missing in prod. | Stale cached content; missing files on deploy.
P3 | CORS | Require ALLOWED_ORIGINS env var in production. | Misconfig risk.
P3 | Session Dates | Add season_start/season_end to team updateSchema. | Coaches cannot edit season after create.
P3 | Bulk Games | Build /games/bulk endpoint with atomic rollback. | Partial schedules on network hiccup.

## v1.0.1 Test Findings
VarsityHub v1.0.1 — Test Findings & Code Audit (Apr 15, 2026)
Source: User manual test notes (LAST 101%.pdf) cross-referenced against current codebase on `main` @ 6012a0c8
# | Finding | Verdict | Severity | Root Cause (file:line) | Required Fix
1 | Approval emails never arrive (ad requests, team requests, org approvals) | BROKEN / PARTIAL | HIGH | server/src/routes/ads.ts:260-272 → email.ts:526-531. Fire-and-forget; if SENDGRID_API_KEY or AD_PENDING_REVIEW template ID is missing on Railway, email silently drops (warning logged only). approvalService.ts:252-129 uses .catch(()=>{}) to silence all failures. | 1) Verify Railway has SENDGRID_API_KEY + all template IDs (AD_PENDING_REVIEW, LEAGUE_PENDING_APPROVAL, COACH_APPROVED, JOIN_REQUEST, VERIFICATION). 2) Add a /health/email endpoint that checks SendGrid connectivity at boot. 3) Log email failures to Sentry with severity=error, not just warn.
2 | Profile shows "PENDING COACH" purple badge — should only show fan/coach | BROKEN (UI) | MEDIUM | app/profile.tsx:620 + L881 — renders "PENDING COACH" when roleRaw==="coach" && approvalStatus !== "APPROVED". Feature Matrix row 271 incorrectly claims this is not rendered. | Change L620 + L881 so pending coaches display "FAN" until APPROVED. Keep internal state (approval_status) unchanged — just swap the display label. Update matrix row 271 to "INCORRECT — pending label still exists, remove it".
3 | Ad Banner image upload fails on iCloud/library photos ("Image Error") | PARTIAL | MEDIUM | components/BannerUpload.tsx:87-168 — expo-image-picker with quality=0.8 and 10MB size check. iCloud error detected L158, but launchImageLibraryAsync is not set to copy-to-cache or force-download before reading. | Pass `allowsEditing: true` and ensure `base64: false` (default) to force a local URI. Add `exif: false`. For iCloud: use `mediaType: "photo"` with `allowsMultipleSelection: false` and handle the "asset not downloaded" case by prompting the user to open the Photos app first. Consider adding a short retry with cache copy.
4 | ALL users can book ads (Rookie bypasses paywall) | PARTIAL (server) | HIGH | server/src/routes/ads.ts:122 checks plan only on POST / (create). submit-for-approval (L282), PUT (L497), reservations (L762) do NOT recheck plan. Client-side gate in app/submit-ad.tsx:137-147 is bypassable if user.preferences.plan is stale or never set. | 1) Add plan guard middleware (requireVeteranOrLegend) to submit-for-approval + reservations routes. 2) On User creation, default preferences.plan = "rookie" explicitly (not undefined). 3) Audit preferences update path after IAP/Stripe purchase — verify plan actually sets.
5 | Coach onboarding SKIPS steps — Settings "Upgrade to Coach" jumps straight to step 3 | BROKEN | HIGH | app/settings/index.tsx:610 — router.push("/onboarding/step-3-league") bypasses step-1-role and step-2-basic. No re-collection of basic profile data (background photo, bio). AuthProvider.tsx:612-623 also re-routes based on approval_status, creating redirect loops. | 1) Navigate to /onboarding/step-2-basic (or step-1 if incomplete), NOT step-3-league. 2) Force markOnboardingIncompleteLocally() BEFORE push so AuthProvider treats user as mid-flow. 3) Guard AuthProvider routing so it does not redirect while user is on /onboarding/*. 4) Add server-side gate: requireOnboarded must check coach-specific fields (org_id, agreement_accepted).
6 | Connect to Organization — verify Search + Create New flows | WORKS (code) / NEEDS RUNTIME TEST | LOW | app/onboarding/step-3-league.tsx:195-225 (search) + L347 (create). Org search hits Organization.search({mode:"nearby"}), create uploads doc then POSTs Organization.create. Join request persists via POST /organizations/join-requests L313. | Runtime QA: (a) search returns nearby orgs, (b) selecting an org emails that org admin (depends on Finding #1 email fix), (c) create new triggers super-admin approval email. If email fix (Finding #1) lands first, this flow should work.
7 | Email verification 6-digit code screen — no Enter / stuck | PARTIAL | MEDIUM | app/verify.tsx:195-201 — explicit "Verify Email" button exists and enables at >=6 chars. Auto-dismiss keyboard at L181. Possible issue: button rendered below keyboard on small devices; no auto-submit on 6-digit entry. | Add auto-submit: call onVerify() automatically when code.length===6 (after a 300ms debounce). Ensure KeyboardAvoidingView keeps the Verify button above the keyboard. Test on iPhone SE / small Android.
8 | Map pin tap should show preview card, second tap navigates to event | NEEDS RUNTIME TEST | LOW | app/game-map.tsx (not fully audited this pass). react-native-maps Marker onPress handlers present but preview/callout behavior not verified. | In game-map.tsx, implement: first tap on Marker = show MapCallout or bottom-sheet preview (title, address, date). Second tap on the callout or a "View Event" button = router.push(`/event/${id}`). Match the 8:21 screenshot layout.

## v1.0.1 Session Summary
v1.0.1 Test Pass — Session Summary
Area | Status | Action Required
Email / Approval System | BROKEN in production | Verify Railway SENDGRID_API_KEY + template IDs. Add /health/email endpoint.
2FA Verification Screen | Needs auto-submit | Auto-submit on 6 digits. Keep Verify button above keyboard.
Coach Onboarding (Settings path) | BROKEN — skips steps | Route to step-2-basic first, not step-3-league. Mark onboarding incomplete before push.
Ad Paywall | BROKEN — Rookie bypass | Add plan check to submit-for-approval + reservations endpoints.
Org Search / Create New | Works (code) | Runtime QA after email fix lands.
Map Pins | Unverified | Implement preview callout → second-tap navigation.
Pending Coach Badge | BROKEN — should hide label | Display "FAN" (not "PENDING COACH") until APPROVED.
Ad Banner Image Upload | iCloud photos fail | Adjust expo-image-picker options; prompt user to pre-download iCloud photos.

## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Feature Matrix
| Table 1 | Feature Matrix
Plan Comparison
| Table 1 | Plan Comparison

## Feature Matrix
VarsityHub — Feature Comparison by Role (Audited v5 FINAL, Apr 13 2026)
Review each feature. Mark Accurate? (Yes/No/Partial) and add your corrections in the Notes column. BLUE rows = suggested rules (not yet implemented).
Legend: Y = Yes (full access) ¦ N = No access ¦ R = Restricted (see notes/plan) ¦ * = Only for own team/org ¦ [NEW] = Suggested rule
1. ACCOUNT & AUTH
#
1 | Sign up (email / Google / Apple) | Y | Y | Y | Y | Y | Y | None | Y
2 | Sign in (email / Google / Apple) | Y | Y | Y | Y | Y | Y | None | Y
3 | Email verification (6-digit code) | Y | Y | Y | Y | Y | Y | Required for most actions | Y
4 | Password reset (6-digit code) | Y | Y | Y | Y | Y | Y | None | Y | ALL CODES ARE SIX DIGITS EXACTLY
5 | Max login attempts: 5 before lockout | Y | Y | Y | Y | Y | Y | Rate limited | Y | CORRECTED: MAX_AUTH_ATTEMPTS = 5 (auth.ts L27), not 10. Lockout window: 15 minutes.
6 | Edit profile (name, bio, avatar, zip) | Y | Y | Y | Y | Y | Y | Display name max 120 chars | Y | CORRECTED: Server validates max(120) at auth.ts L952, not 15 chars. No frontend maxLength enforced.
7 | Set / change username | Y | Y | Y | Y | Y | Y | 3-20 chars, lowercase+nums+dots+underscores | Y | CORRECTED: auth.ts L953/L1265 + edit-username.tsx L48 enforce 3-20 chars, not 1-25.
8 | Change password | Y | Y | Y | Y | Y | Y | None | Y
9 | Delete account | Y | Y | Y | Y | Y | Y | None | Y
10 | Set privacy (public / private profile) | Y | Y | Y | Y | Y | Y | None | Y
11 | Core values profile section | Y | Y | Y | Y | Y | Y | None | Y
2. FEED & POSTS
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections | v1.0.1 Status (Apr 15, 2026)
12
13 | View followed-users feed | Y | Y | Y | Y | Y | Y | Auth required | Y
14 | View followed-teams feed | Y | Y | Y | Y | Y | Y | Auth required | Y
15 | View trending posts | Y | Y | Y | Y | Y | Y | None | Y
16 | Create post (text and/or media) | Y | Y | Y | Y | Y | Y | Email verified + onboarded | Y
17 | Edit own post | Y | Y | Y | Y | Y | Y | None | Y
18 | Delete own post | Y | Y | Y | Y | Y | Y | None | Y
19 | Undo post (within window) | Y | Y | Y | Y | Y | Y | None | Y
20 | Upvote / bookmark post | Y | Y | Y | Y | Y | Y | Auth required | Y | Upvote/bookmark works correctly. (The stale 410 note referred to UNDO endpoint, now also fixed in v1.0.2.) | ACCURATE: upvote + bookmark endpoints at posts.ts:1205, 1273 both active.
21 | Comment on post | Y | Y | Y | Y | Y | Y | Subject to author's comment permission | Y
22 | Edit / delete own comment | Y | Y | Y | Y | Y | Y | None | Y
23 | Share post | Y | Y | Y | Y | Y | Y | None | Y
24 | Create poll in post | Y | Y | Y | Y | Y | Y | None | Y
25 | Vote in poll | Y | Y | Y | Y | Y | Y | Auth required | Y
26 | Pin post on team feed | N | N | Y* | Y | Y* | Y | Coach/manager of team | Y
27 | @mention users in post | Y | Y | Y | Y | Y | Y | None | Y
28 | Caps in posts allowed (no spam filter) | Y | Y | Y | Y | Y | Y | Caps detection removed for fans | Y
3. TEAMS
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections
29 | View / search all teams | Y | Y | Y | Y | Y | Y | None | Y
30
31 | Follow / unfollow team | Y | Y | Y | Y | Y | Y | Auth required | Y
32 | Join public team | Y | Y | Y | Y | Y | Y | Auth required | N | CONFIRMED: No public/private team distinction in schema. All teams are org-scoped, invite-only. Feature does not exist in codebase.
33 | Request to join private team | Y | Y | Y | Y | Y | Y | Auth required | N | CONFIRMED: No team privacy field in Prisma schema. All teams use invite-based membership (TeamInvite model). Feature does not exist.
34 | Accept / decline team invite | Y | Y | Y | Y | Y | Y | Auth required | Y
35 | Create team | N | N | Y | Y | Y | Y | Rookie: 2 max, Veteran/Legend: unlimited | Y
36 | Edit team details | N | N | Y* | Y | Y* | Y | Owner/manager of team | Y
37 | Delete team | N | N | Y* | Y | Y* | Y | Owner of team | Y
38 | View team roster | R | Y | Y | Y | Y | Y | Team member/coach/admin | Y
39 | View team contacts | N | Y | Y | Y | Y | Y | Team member | Y
40 | Invite members to team | N | N | Y* | Y | Y* | Y | Owner/manager/coach/asst_coach | Y
41 | Remove members from team | N | N | Y* | Y | Y* | Y | Owner/manager/coach | Y
42 | Approve team join requests | N | N | Y* | Y | Y* | Y | Owner/manager/coach | Y
43 | Manage team seasons | N | N | Y* | Y | Y* | Y | Owner/manager/coach | Y | season_start/season_end editable via PATCH /teams/:id. Fixed in v1.0.2. | FIXED v1.0.2
44 | Bulk schedule games for team | N | N | Y* | Y | Y* | Y | Owner/manager/coach | Y | POST /games/bulk with $transaction rollback; manage-season.tsx uses Game.bulkCreate(). | FIXED v1.0.2
4. ORGANIZATIONS
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections
45 | View / search organizations | Y | Y | Y | Y | Y | Y | Approved orgs only (unless admin) | Y
46 | Request to join organization | Y | Y | Y | Y | Y | Y | Auth required | Y
47
48 | Create organization | N | N | Y | Y | Y | Y | Email verified + onboarded | Y
49 | Edit organization details | N | N | N | Y | Y | Y | Owner/manager of org | Y
50 | Invite members to organization | N | N | N | Y | Y | Y | Owner/manager of org | Y
51 | Manage org members & roles | N | N | N | Y | Y | Y | Owner/manager of org | Y
52 | Approve coach join requests | N | N | N | Y | Y | Y | Org owner/manager | Y
53 | Reject coach join requests | N | N | N | Y | Y | Y | Org owner/manager | Y
54 | View pending coaches list | N | N | N | Y | Y | Y | Org owner/manager | Y
55 | Approve organization join requests | N | N | N | Y | Y | Y | Org owner/manager | Y
56 | Request admin approval for league | N | N | Y | Y | Y | Y | Org owner | Y
57 | Org rejection 48hr cooldown before reapply | Y | Y | Y | Y | Y | Y | Auto-enforced | Y | IMPLEMENTED: 48hr cooldown on both POST / (L331) and POST /create (L464) in organizations.ts. rejected_at field added to schema.
58 | Coach rejection 48hr cooldown before reapply | N | N | Y | Y | Y | Y | Stored in user preferences | Y | IMPLEMENTED in v1.0.2: User.rejected_at field + REJECTION_COOLDOWN_MS (48h). Enforced on /auth/upgrade-to-coach and /auth/coach/reapply. | FIXED v1.0.2
59 | Coach re-application after rejection | N | N | Y | Y | Y | Y | POST /:id/coaches/:userId/reapply | Y | IMPLEMENTED in v1.0.2: POST /auth/coach/reapply endpoint. Client API User.reapplyCoach(). pending-approval.tsx surfaces Try Again button. | FIXED v1.0.2
60 | Org approval → routes to coach onboarding | N | N | Y | Y | Y | Y | Push notification directs to coach agreement | Y | FIXED v1.0.2: Settings → Upgrade to Coach routes to step-2-basic. AuthProvider guarded from yanking users off /onboarding/*. Push notifications deep-link to coach-agreement. | FIXED v1.0.2
61 | Admin cannot approve coach without org | N | N | N | Y | N | Y | Returns 400 if no org context | Y
5. GAMES & SCORES
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections
62 | View all games | Y | Y | Y | Y | Y | Y | Approved games only (public) | Y
63 | View game details / photos / highlights | Y | Y | Y | Y | Y | Y | None | Y
64 | View game on map | Y | Y | Y | Y | Y | Y | None | Y | FIXED v1.0.2: map_view=true query restricts to games in next 7 days. Past games drop off map in real time. First tap shows callout; second tap navigates. | FIXED v1.0.2
65
66 | Create game (requires team membership) | N | N | Y* | Y | Y* | Y | Must be coach/manager/owner of team | Y
67 | Edit game | N | N | Y* | Y | Y* | Y | Coach/org owner of team | Y
68 | Submit / update game score | N | N | Y* | Y | Y* | Y | Coach/manager of team | Y
69 | Cancel game | N | N | Y* | Y | Y* | Y | Coach of team | Y
70 | Upload game photos | Y | Y | Y | Y | Y | Y | Auth required | Partial | Upload capability works. Previous note was about event/map filtering, not photo behavior — semantically mixed. Past games now filtered at games.ts L365.(MAKE SURE THIS WORKS)
6. EVENTS
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections
71 | View / search events | Y | Y | Y | Y | Y | Y | Approved events only | Y
72 | View event details | Y | Y | Y | Y | Y | Y | None | Y
73 | Filter events by location / radius | Y | Y | Y | Y | Y | Y | None | Y
74 | RSVP to event | Y | Y | Y | Y | Y | Y | Auth required; subject to capacity | Y
75
76 | Create community event (fan) | Y | Y | Y | Y | Y | Y | Rookie: 2 pending max; Veteran+: unlimited | Partial | ALL FANS CAN PITCH EVENTS TO ANY TEAM. ITS UP TO EMAIL ADMIN TO APPROVE
77 | Create team event | N | N | Y* | Y | Y* | Y | Coach of team | Partial | Feature exists. Role text is simplified vs actual admin/org/coach permission logic in events.ts. Org owner can create events for teams in their org.( IS THIS SAFE AND SECURE. )
78 | Edit / cancel own event | Y* | Y* | Y* | Y | Y* | Y | Creator or team coach | Y
79 | Approve / reject pending events | N | N | Y* | Y | Y* | Y | Coach/org admin | Y
80 | Request to host event | Y | Y | Y | Y | Y | Y | None | Partial | Real feature, Fan events get pending status, coaches/elevated roles auto-approve. Server logic is more nuanced than a simple Y. (WAT ELSE NEEDS TO BE DONE )
81 | Create events with past dates (record-keeping) | N | N | N | Y | Y | Y | Past dates allowed | Y | Server Zod validation blocks past dates: date must be >= now. Past-date events cannot be created by anyone. Fans cannot create events — only pitch (approval_status: pending).
7. STORIES & HIGHLIGHTS
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections
82 | View stories feed | Y | Y | Y | Y | Y | Y | None | Y
83 | View highlights (media-only posts) | Y | Y | Y | Y | Y | Y | Only posts with media shown | Y
84 | Create story (24hr expiry) | Y | Y | Y | Y | Y | Y | Auth + email verified | Y
85 | Create game story (geofenced) | Y | Y | Y | Y | Y | Y | Must be within 2km of event; error msg updated | Y | Server enforces 2km geofence for game stories. User spec: same 2km radius applies to posts tagged to a game. | ACCURATE: unchanged
86 | Upload game highlight | Y | Y | Y | Y | Y | Y | Auth required | Partial | HIGHLIGHTS AS IN THE TAB HIGHLIGHTS IN THE BOTTOM LEFT OF THE APP.
87
88 | Highlights: admin/org owner see worldwide | Y | Y | Y | Y | Y | Y | Others limited to 100km radius | Y | STALE: 100km hard cap removed. Now uses worldwide pool + country/local ranking boosts only (highlights.ts L25, L182). No geographic filter, only scoring signals.
8. MESSAGING
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections
89 | Send / receive direct messages | Y | Y | Y | N | N | N | Auth + email verified; DM privacy applies | Y | Confirmed: No role-based DM restrictions in messages.ts. All authenticated users can DM based on recipient dm_policy preference (everyone/following/no_one). No Email Admin or Org Owner block.
90 | View message threads (50 DM / 100 group per request) | Y | Y | Y | N | N | Y | Auth required | Y | CORRECTED: DMs capped at 50/request (messages.ts L62). Group chats at 100 (group-chats.ts L105). No 300 anywhere in code.
91 | View unread count | Y | Y | Y | Y | Y | Y | Auth required | Y
92 | Create group chat | N | N | Y | Y | Y | Y | Auth required | Y
93 | Join group chat (invite-based) | N | Y | Y | Y | Y | Y | Auth required | Y | NO JOIN ENDPOINT: group-chats.ts only has GET /, GET /:chatId/messages, POST /:chatId/messages, POST /:chatId/read, POST / (create). Members added only at creation by coach/manager.
94 | DM restrictions (everyone / followers / none) | Y | Y | Y | Y | Y | Y | User setting | Y
9. ADS
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections
95 | View ads in feed | Y | Y | Y | Y | Y | Y | None | Y
96 | Create ad (draft) — Veteran/Legend/Admin only | Y | Y | Y | Y | Y | Y | Veteran/Legend plan or Admin required | Y | FIXED v1.0.2: plan gate enforced on BOTH POST /ads (create) AND POST /ads/:id/submit-for-approval (was create-only before). enforceAdPlan() helper in ads.ts. | FIXED v1.0.2
97 | Edit own ad | Y | Y | Y | Y | Y | Y | Ad owner | Y
98 | Submit ad for approval | Y | Y | Y | Y | Y | Y | 56-day booking horizon | Y
99 | View my ads dashboard | Y | Y | Y | Y | Y | Y | Ad creator | Y
100 | View ad calendar / available slots | Y | Y | Y | Y | Y | Y | Ad creator | Y
101 | Book ad slots (Stripe payment) | Y | Y | Y | Y | Y | Y | Max 2 slots/date/zip | Y
102
103 | Ad radius: 10km | Y | Y | Y | Y | Y | Y | Geofenced delivery | Y
104 | Ad creation limit: 10/day | Y | Y | Y | Y | Y | Y | Rate limited | Y
105 | Ad approved → goes active if already paid | Y | Y | Y | Y | Y | Y | Skips payment step | Y | FIXED v1.0.2: approvalService activates already-paid ads; unpaid stays pending_approval with notification "Tap to complete payment." Stripe paid re-verify inside tx closes TOCTOU. | FIXED v1.0.2
106 | Ad approval email includes receipt details | Y | Y | Y | Y | Y | Y | Amount, dates, purpose | Y
107 | Approve / reject ads | N | N | N | N | N | Y | Admin only | Y
108 | Cancel ad | Y | Y | Y | Y | Y | Y | Ad creator; pending/draft only | Y | If ad is cancelled and already paid for, no refund
10. NOTIFICATIONS
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections
109 | View notifications | Y | Y | Y | Y | Y | Y | Auth required | Y
110 | Receive push notifications | Y | Y | Y | Y | Y | Y | Auth required | Partial | Capability exists. Token registered at sign-in (sign-in.tsx L89) and AuthProvider (L405). But delivery depends on valid saved Expo token (notifications.ts L33). Not guaranteed for all authenticated users.
111 | Manage notification preferences | Y | Y | Y | Y | Y | Y | Auth required | Y
112 | Org approved → directs to coach onboarding | N | N | Y | Y | Y | Y | Deep link to /onboarding/coach-agreement | Partial | Deep link exists in NotificationTapHandler, but full resulting coach onboarding flow is not robust enough for a clean Y. Same brittleness as row 75 (#60).
113 | Coach approved notification (conditional type) | N | N | Y | Y | Y | Y | JOIN_REQUEST_APPROVED or COACH_APPROVED | Y
11. SEARCH & DISCOVERY
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections
114 | Search users | Y | Y | Y | Y | Y | Y | None | Y
115
116 | Search games / events | Y | Y | Y | Y | Y | Y | None | Y
117 | [REMOVE] Browse community directory — does not exist in codebase | Y | Y | Y | Y | Y | Y | None | N | REMOVE FROM MATRIX: no "community directory" feature exists. No route, schema, or UI. Spec artifact — delete row or replace with the existing user/team/event search. | REMOVE ROW
118 | Filter by location / zip / sport | Y | Y | Y | Y | Y | Y | None | Partial | Sport appears in results but no dedicated sport filter control in UI. Users can text-search for sport names only. SPORT FILER IS SMART, BUT PEOPLE REALLY WANT TO GO TO EVENTS NEAR THEM
119 | Browse nearby events on map | Y | Y | Y | Y | Y | Y | None | Y
12. MODERATION & SAFETY
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections
120 | Report user / post / comment / message | Y | Y | Y | Y | Y | Y | Auth required; 10/hr limit | Y
121
122 | View own blocked users list | Y | Y | Y | Y | Y | Y | Auth required | Y
123 | View pending reports (admin) | N | N | N | N | N | Y | Admin only | Y
124 | Issue warning to user (3 reports → warning) | N | N | N | N | N | Y | Admin only | Y | FIXED v1.0.2: feature text corrected to match moderation.ts constants. | FIXED v1.0.2 (text corrected)
125 | Issue strike to user (5 reports → strike) | N | N | N | N | N | Y | Admin only | Y | FIXED v1.0.2: feature text corrected to match moderation.ts constants. | FIXED v1.0.2 (text corrected)
126 | Suspend user (8 reports → 7-day suspension) | N | N | N | N | N | Y | Admin only | Y | FIXED v1.0.2: feature text corrected to match moderation.ts constants. | FIXED v1.0.2 (text corrected)
127 | Ban user (12 strikes → permanent ban) | N | N | N | N | N | Y | Admin only | Y | FIXED v1.0.2: feature text corrected to match moderation.ts constants. | FIXED v1.0.2 (text corrected)
128 | Delete any content (admin) | N | N | N | N | N | Y | Admin only | Y
129 | Spike alert at 10+ pending reports | N | N | N | N | N | Y | Auto-notifies admins | Y
13. ADMIN DASHBOARD
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections
130 | View admin dashboard & platform stats | N | N | N | N | N | Y | Admin only | Y
131 | View verified / banned user counts | N | N | N | N | N | Y | Admin only | Y
132 | View pending ads / coaches / leagues | N | N | N | N | N | Y | Admin only | Y | Pricing structure exists. Hour count display for 'how long ad was live' not verified in frontend — needs runtime check.
133 | View admin activity log | N | N | N | N | N | Y | Admin only | Y
134 | Manage all users (search, edit, suspend) | N | N | N | N | N | Y | Admin only | Y
135 | Approve coaches (requires org context) | N | N | N | N | N | Y | Admin only; coach must have org | Y
136 | Approve / reject organizations | N | N | N | N | N | Y | Admin only | Y
137 | View admin reports | N | N | N | N | N | Y | Admin only | Y
138 | View transaction log | N | N | N | N | N | Y | Admin only | Y
139 | View founder / analytics metrics | N | N | N | N | N | Y | Admin only | Y
14. SUBSCRIPTIONS & BILLING
#
140 | View current plan details | Y | Y | Y | Y | Y | Y | None | Y
141 | Upgrade to Veteran ($0.99/mo per team, min 3 teams) | Y | Y | Y | Y | Y | Y | Requires 3+ teams | Y | Correct as written ($0.99 per team, Veteran tier, >2 teams). Text already updated from stale $1 value. | ACCURATE
142 | Upgrade to Legend ($29.99/yr) | Y | Y | Y | Y | Y | Y | Unlimited everything; first 100 get $14.99 | Partial | $29.99/yr is correct. "first 100 get $14.99" is DB/store config (FIRST100LEGENDS promo), not repo-provable.( MAKE THE 14.99 PROMO ACCURATE, WE HAVE IAP AND IN STRIPE)
143 | Apple IAP (Product ID 6761790811 / TOP_TIER) | Y | Y | Y | Y | Y | Y | iOS in-app purchase for Legend | Y | IAP verified by user. v1.0.2 added apple_transaction_id @unique partial index preventing double-processing. | FIXED v1.0.2
144 | Manage subscription / update billing | Y | Y | Y | Y | Y | Y | Auth required | Y
145 | View billing history | Y | Y | Y | Y | Y | Y | Auth required | Y | FIXED v1.0.2: GET /payments/history + app/settings/billing-history.tsx. Linked from manage-subscription. Auth-scoped to current user. | FIXED v1.0.2
146 | Cancel subscription | Y | Y | Y | Y | Y | Y | Auth required | Y
147 | Apply promo code (FIRST100LEGENDS = 50% off) | Y | Y | Y | Y | Y | Y | During checkout; max 100 uses | DB/Store Verify | PromoCode table and route exist. Exact code string "FIRST100" and 50% discount are DB runtime values, not repo-provable. PROVE IN REPO
15. ONBOARDING
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections
148 | Select role (Fan / Coach) | Y | Y | Y | Y | Y | Y | During registration | Y | 2FA mandatory for email/password signup. Apple/Google OAuth bypass 2FA (standard pattern). | ACCURATE
149 | Complete basic profile | Y | Y | Y | Y | Y | Y | Email verified | Y | Basic profile: name, username, avatar, DOB, zip, bio, background photo in step-2-basic. Background photo input present. | ACCURATE
150
151 | Join / create organization | N | N | Y | Y | Y | Y | Coach onboarding | Y
152 | Coach agreement acceptance | N | N | Y | Y | Y | Y | Required for coaches | Y | FIXED v1.0.2: server-enforced via requireOnboarded returning 403 COACH_AGREEMENT_REQUIRED if coach_agreement_accepted_at is null. Client UI still prompts. | FIXED v1.0.2
153 | Pending approval screen (coach) | N | N | Y | Y | Y | Y | After coach request | Partial | TWO STATES: pending-approval.tsx (join-request waiting) and league-pending-approval.tsx (org-approval waiting). AuthProvider.tsx L363 now distinguishes them. Not a single screen.
154 | League pending approval screen | N | N | Y | Y | Y | Y | After org creation | Y
16. SETTINGS
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections
155 | Edit username | Y | Y | Y | Y | Y | Y | Auth required | Y
156 | Change privacy (public / private) | Y | Y | Y | Y | Y | Y | Auth required | Y
157 | Manage followed teams | Y | Y | Y | Y | Y | Y | Auth required | Y
158 | Manage favorites | Y | Y | Y | Y | Y | Y | Auth required | Y | Matrix text "Manage favorites" is misleading — code only manages saved/bookmarked POSTS, not team/people/org favorites. Either rename row to "Saved posts" or build broader favorites. | MATRIX TEXT MISLEADING
159
160 | Appearance / theme settings | Y | Y | Y | Y | Y | Y | None | Y
161 | Submit feedback | Y | Y | Y | Y | Y | Y | None | Y
162 | Contact support | Y | Y | Y | Y | Y | Y | None | Y
163 | View privacy policy / TOS / DMCA / core values | Y | Y | Y | Y | Y | Y | None | Y
164 | Reset password from settings | Y | Y | Y | Y | Y | Y | Auth required | Y
165 | DM restrictions setting | Y | Y | Y | Y | Y | Y | Auth required | Y
17. SUGGESTED RULES (NOT YET IMPLEMENTED)
# | Feature | Fan | Athlete | Coach | Email Admin | Org Owner | Super Admin | Plan Restriction | Accurate? | Your Notes / Corrections
166 | [NEW] Rate limit post creation (e.g. 20/day per user) | Y | Y | Y | Y | Y | Y | Prevent spam flooding feed | Y
167
168 | [NEW] Auto-expire draft ads after 30 days | Y | Y | Y | Y | Y | Y | Clean up abandoned drafts | Y
169 | [NEW] Group chats team-scoped only (NOT org-wide) | Y | Y | Y | Y | Y | Y | Prevent abuse of group messaging | N | SPEC CLARIFICATION: group chats are per-team, not org-wide. Code: group-chats.ts has POST / (create) with members added only at creation. No org-wide group exists. Remove "50 members" — replace with "team-scoped only". | SPEC UPDATE NEEDED
170 | [NEW] Max file upload size per post (e.g. 50MB) | Y | Y | Y | Y | Y | Y | Storage/bandwidth control | Y | MAKE SURE ITS SAFE AND SEUCRE. USE LEAST AMOUNT OF DATA AS POSSIBLE
171 | [NEW] Coach must verify org email domain | N | N | Y | Y | Y | Y | Extra trust layer for coach approval | N | I DONT KNOW WHA THIS MEANS
172 | [NEW] Auto-archive events 3 days after date | Y | Y | Y | Y | Y | Y | Keep event listings current | Y | FIXED v1.0.2: events list filter changed to gte(now - 3d). 3 days now matches spec. | FIXED v1.0.2
173 | [NEW] Require profile photo to create posts | Y | Y | Y | Y | Y | Y | Reduce anonymous spam | N
174 | [NEW] Weekly email digest of team activity | Y | Y | Y | Y | Y | Y | Engagement/retention feature | N
175 | [NEW] Allow team-level comment moderation | N | N | Y* | Y | Y* | Y | Coach can moderate their team's posts | N
176 | [NEW] Ad refund policy (within 24hrs of booking) | Y | Y | Y | Y | Y | Y | Consumer protection | Y | Current policy: no refunds on ad bookings (except SLOT_FULL auto-refund with amount tracking as of v1.0.2). | ACCURATE + v1.0.2 refund amount tracked
177 | [NEW] Rate limit DMs (e.g. 100/hr) | Y | Y | Y | Y | Y | Y | Prevent message spam | Y
CODEBASE AUDIT RESULTS (April 13, 2026)
Status | Item |  |  | Detail
FIXED THIS SESSION | Highlights 100km radius removed |  |  | highlights.ts: RADIUS_KM hard filter replaced with LOCAL_BOOST_KM ranking signal. Country posts first, global fill. No content hidden by distance.
FIXED THIS SESSION
FIXED THIS SESSION | Org rejection 48hr cooldown |  |  | schema.prisma: added rejected_at field. approvalService.ts sets it on rejection. Both org creation endpoints return 429 within 48hrs of rejection.
NOT YET FIXED | Mandatory first team after approval |  |  | Coach onboarding flow allows skipping team creation. Notes require one team mandatory.
NOT YET FIXED | Ad payment flow after approval |  |  | Approval notification says 'tap to complete payment' but payment screen reachability from notification unverified. Needs runtime test.
NOT YET FIXED | Congratulations copy after approval |  |  | pending-approval.tsx shows 'Welcome to...' not 'Congratulations on being accepted\!' as specified in notes.
NOT YET FIXED | Community directory (Feature #117) |  |  | Does not exist in codebase. Remove from matrix or build.
NEEDS DECISION | Promo code string |  |  | FIRST100LEGENDS vs FIRST100 — stored in DB only, not in source code. Verify and update in database.
NEEDS DECISION | DM role restrictions |  |  | No role-based DM blocks exist. Email Admin/Org Owner can DM freely. XLSX marked N — confirm intended behavior.
NEEDS DECISION | Coach badge feature |  |  | No badge rendering logic found in frontend profile screens. May need to be built.
NEEDS DECISION | Zip code min length |  |  | Client requires 5+ chars (step-2-basic.tsx:276). Some countries use 3-4 digit postal codes.
NEEDS DECISION | Keyboard gap in onboarding |  |  | KeyboardAvoidingView configured with offset=64 on iOS. May need per-device tuning. Runtime test required.
CONFIRMED WORKING | Notification badge on bell icon |  |  | Badge renders on bell (NotificationBellIcon.tsx:26-29), not profile. Correct.
CONFIRMED WORKING | Report captures post content |  |  | reports.ts:77-95 stores full content+media in targetContext. Support sees reported content.
CONFIRMED WORKING | Coach approval deep link routing |  |  | NotificationTapHandler routes coach_approved to /onboarding/coach-agreement.
CONFIRMED WORKING
CONFIRMED WORKING | No 'pending coach' tag in UI |  |  | Not found anywhere in frontend. Only fan/coach labels displayed.
CONFIRMED WORKING | No public/private team distinction |  |  | Schema has no team privacy field. All teams are invite-only.
CONFIRMED WORKING | Dark mode text colors |  |  | No hardcoded #000/#111/#333/black text colors found in app/*.tsx.
CONFIRMED WORKING | Fan event creation = pitch only |  |  | Fans get pending status. Coaches auto-approve. Server enforces correctly.
CONFIRMED WORKING | Past-date events blocked |  |  | Zod schema refine rejects event dates in the past.
CONFIRMED WORKING | Email centralized via EmailService |  |  | No sgMail.send outside email service. All routes use sendTemplateEmail.
18. ADDED IN v1.0.2 AUDIT
178.0 | Ban list — banned users cannot send DMs | N | N | N | N | N | N | Banned field enforced | Y | messages.ts now 403s with USER_BANNED if user.banned=true or banned_until > now. | NEW v1.0.2
179.0 | Coach agreement — server-enforced gate | N | N | Y | Y | Y | Y | requireOnboarded 403 if unsigned | Y | requireOnboarded.ts returns 403 COACH_AGREEMENT_REQUIRED for APPROVED coaches missing coach_agreement_accepted_at. | NEW v1.0.2
180.0 | Coach rejection 48hr cooldown | N | N | Y | Y | Y | Y | rejected_at field + REJECTION_COOLDOWN_MS | Y | approvalService.rejectCoach persists rejected_at + reason. auth.ts upgrade-to-coach and /coach/reapply check cooldown. | NEW v1.0.2
181.0 | Coach re-apply endpoint (POST /auth/coach/reapply) | N | N | Y | Y | Y | Y | Rejected coaches only, after cooldown | Y | Client API: User.reapplyCoach(). Returns 429 with retry_after_hours if still within cooldown. | NEW v1.0.2
182.0 | Ad plan gate — enforced on submit-for-approval | Y | Y | Y | Y | Y | Y | Veteran/Legend or admin | Y | Previously only checked on POST /ads (create draft). Now also re-checked on submit-for-approval. | NEW v1.0.2
183.0 | Email health check endpoint /health/email | N | N | N | N | N | Y | Admin-only, X-Health-Check-Secret header | Y | Returns 503 if SendGrid missing or critical templates not configured. Use for post-deploy smoke tests. | NEW v1.0.2
184.0 | Apple IAP double-process protection | Y | Y | Y | Y | Y | Y | DB-level unique constraint | Y | transactionLog.apple_transaction_id has partial unique index. Second write with same ID fails fast. | NEW v1.0.2 (requires migration)
185.0 | Ad activation race protection | N | N | N | N | N | Y | Serializable tx + conditional updateMany | Y | payments.ts uses updateMany with status filter — admin reject mid-payment fails activation gracefully. | NEW v1.0.2
186.0 | Stripe paid re-verify on finalize | Y | Y | Y | Y | Y | Y | sessions.retrieve() before plan update | Y | Closes TOCTOU where stale session objects could carry an old paid flag. | NEW v1.0.2
187.0 | 2FA code auto-submit at 6 digits | Y | Y | Y | Y | Y | Y | None | Y | verify.tsx auto-submits after 6-digit entry with 150ms debounce. returnKeyType=done for hardware submit. | NEW v1.0.2
188.0 | Pending Coach profile badge — suppressed pre-approval | Y | Y | Y | Y | Y | Y | None | Y | profile.tsx shows "FAN" label for coaches with approval_status !== APPROVED. Internal state unchanged. | NEW v1.0.2
189.0 | Map pin preview callout | Y | Y | Y | Y | Y | Y | None | Y | EventMap.tsx — first tap shows callout with title/location/date, second tap navigates to event. | NEW v1.0.2
190.0 | iCloud photo picker friendlier error | Y | Y | Y | Y | Y | Y | None | Y | BannerUpload.tsx — broader iCloud error detection + user-facing prompt to pre-download photo. | NEW v1.0.2
191.0 | Rate-limit disable env var unified | N | N | N | N | N | Y | Dev/stage only | Y | DISABLE_RATE_LIMITING now accepts 1/true/yes/on in both rateLimiters.ts and auth.ts. No more silent half-enforcement. | NEW v1.0.2
192.0 | Geocoding fails loud in production | N | N | N | N | N | Y | Admin-visible logs | Y | Missing GOOGLE_MAPS_API_KEY logs at error level in prod. API status (ZERO_RESULTS/REQUEST_DENIED/etc) surfaced in logs. | NEW v1.0.2
19. STILL OUTSTANDING (v1.0.2 backlog)
193.0 | Undo post endpoint returns 410 — restore path broken | Y | Y | Y | Y | Y | Y | None | Y | posts.ts:1415 returns 410 "Post deletion is final". POST_UNDO_WINDOW_MS constant exists but code rejects restore. Product decision needed. | FIXED v1.0.2: /posts/:id/restore now enforces POST_UNDO_WINDOW_MS (5min); returns 410 UNDO_WINDOW_EXPIRED past window.
194.0 | Team season dates editable after creation | N | N | Y | Y | Y | Y | Owner/manager | Y | teams.ts updateSchema missing season_start/season_end. Coaches stuck with initial dates. | FIXED v1.0.2: teams.ts updateSchema now accepts season_start/season_end; PATCH writes them.
195.0 | /games/bulk endpoint with atomic rollback | N | N | Y | Y | Y | Y | Owner/manager | Y | manage-season.tsx loops GameAPI.create(). No atomic bulk endpoint. Partial failures leave dirty state. | FIXED v1.0.2: POST /games/bulk endpoint added. Atomic $transaction, all-or-nothing. Max 30 games/call. manage-season.tsx uses it.
196.0 | Billing history screen in app | Y | Y | Y | Y | Y | Y | Auth required | Y | manage-subscription.tsx has cancel/manage links only. Build history view or remove row from matrix. | FIXED v1.0.2: /payments/history endpoint + app/settings/billing-history.tsx screen + link from manage-subscription.
197.0 | Rejected ORG 48hr cooldown | N | N | Y | Y | Y | Y | Stored on org record | Y | Same pattern as coach cooldown (rejected_at + REJECTION_COOLDOWN_MS). Schema + service needed. | FIXED v1.0.2: Organization.rejected_at + rejection_reason. Cooldown check on POST / and POST /create (429 with retry_after_hours).
198.0 | Past-week map filter (games older than 7 days) | Y | Y | Y | Y | Y | Y | None | Y | Test note: "map should only reflect games that are the week of in real time". Current filter is "gte today". Needs definition + games.ts update. | FIXED v1.0.2: games list accepts map_view=true → restricts to games in next 7 days. game-map.tsx passes it.
199.0 | Auto-archive events 3 days after event date | Y | Y | Y | Y | Y | Y | None | Y | Spec updated from 7 → 3 days. cron job or query filter needed. | FIXED v1.0.2: events list filter changed to gte (now - 3 days). Events remain visible for 72h after, then drop.
200.0 | Email domain verify for coach org match | N | N | Y | Y | Y | Y | Extra trust layer | N | Deferred — needs product decision on strictness (block vs warn). | TODO
20. ADDED IN v1.0.2 PASS 2 (final hardening)
201.0 | Undo post — restore within 5min window | Y | Y | Y | Y | Y | Y | Author only, POST_UNDO_WINDOW_MS=5min | Y | posts.ts /restore checks author + window; returns 410 UNDO_WINDOW_EXPIRED past 5min. | NEW v1.0.2
202.0 | Team season dates editable after creation | N | N | Y* | Y | Y* | Y | Owner/manager of team | Y | teams.ts updateSchema now accepts season_start/season_end (nullable to clear). | NEW v1.0.2
203.0 | POST /games/bulk — atomic schedule create | N | N | Y* | Y | Y* | Y | Max 30 games/call, tx rollback on fail | Y | games.ts: serializable transaction creates all-or-nothing. Client: Game.bulkCreate(). manage-season.tsx uses it. | NEW v1.0.2
204.0 | Org rejection 48hr cooldown + 429 | N | N | Y | Y | Y | Y | rejected_at + REJECTION_COOLDOWN_MS | Y | POST /organizations and /organizations/create return 429 REJECTION_COOLDOWN within window. | NEW v1.0.2
205.0 | Games map filter: week-of only | Y | Y | Y | Y | Y | Y | ?map_view=true restricts to next 7 days | Y | games.ts list handler adds date range when map_view=true. Past games drop off map in real time. | NEW v1.0.2
206.0 | Event auto-archive 3 days after date | Y | Y | Y | Y | Y | Y | Default listings only; admin can still see | Y | events.ts list filter changed to gte(now - 3d). Recap photos/posts stay visible 72h post-event. | NEW v1.0.2
207.0 | Billing history screen | Y | Y | Y | Y | Y | Y | Auth required; own transactions only | Y | GET /payments/history returns user TransactionLog rows. app/settings/billing-history.tsx consumes it. Linked from manage-subscription. | NEW v1.0.2

## Plan Comparison
VarsityHub Subscription Plan Comparison (Updated Apr 2026)
Feature / Limit | Rookie (Free) | Veteran ($0.99/mo/team) | Legend ($29.99/yr) | Accurate? | Your Notes
Price | $0 | $0.99/mo per team over 2 | $29.99/year (first 100: $14.99) | Y | CORRECTED: $0.99 not $1.00. payments.ts L234: unit_amount=99 cents.
Max Teams Owned | 2 | Unlimited (3+ billable) | Unlimited | Y
Max Authorized Users Per Team | 1 | 5 | Unlimited | Y
Max Roster Size Per Team | 50 | 100 | Unlimited | Y
Org Auth User Strategy | Fixed 1 user | 5 per team | Unlimited | Y
Community Events (pending) | 8 pending max | Unlimited | Unlimited | Wrong → Fixed | ALL FAN EVENTS HAVE TO GO THROUGH THE SAME APPROVAL PROCESS NO MATTER WAT TIER THE COACH IS
Extracurricular Teams | No | No | Yes (Theater, Chess, Debate, etc.) | Y
Ad Slot Booking | No | Yes | Yes | Wrong → Fixed | CORRECTED: Ad creation requires Veteran/Legend plan or admin. ads.ts L114-122: 403 PLAN_REQUIRED for Rookie users.
Ad Pricing | $4.99/wk weekday, $7.99/wk weekend | Same | Same | Y
Ad Radius | 10km | 10km | 10km | Y
Apple IAP Product ID | N/A | MIDTIER | TOPTIER / 6761790811 | DB/Store Verify | Code mapping exists (payments.ts L2341) but live product IDs need App Store Connect verification. MAKE SURE THESE WORKS ALL VALUES ARE ALREADY ACCURATE
Promo Code | N/A | N/A | FIRST100 (50% off, max 100) | DB/Store Verify | PromoCode table and route exist. Exact code and discount are DB runtime values.
All Core Features (feed, DM, search) | Yes | Yes | Yes | Y
Message History | 50 per request (paginated) | 50 per request (paginated) | 50 per request (paginated) | Wrong → Fixed | CORRECTED: No "300" limit in code. messages.ts L62: Math.min(..., 50) hard cap per API call. Paginated with cursor.
Moderation | 3 warn, 5 strike, 8 suspend, 12 ban | Same | Same | Wrong → Fixed | CORRECTED: moderation.ts L12-15 thresholds are 3/5/8/12, not 1/2/3.